## Sprint-2
13April - 24 April
TASK # | DESCRIPTION | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10
1 | Create visuals | bar: DAY 1 to DAY 2
2 | Implementation of Landing page Functionality | bar: DAY 2 to DAY 4
3 | Implementation of cluster functionality | bar: DAY 3 to DAY 6
4 | Implementation of New job functionality: Sprint 2 task | bar: DAY 6 to DAY 10
5 | Test case writing for Home Page | bar: DAY 1
6 | Test case writing for Cluster Configuration Page | bar: DAY 2
7 | Test case writing for Define Cluster Configuration Page | bar: DAY 3
8 | Test case writing for Define Data Quality Page | bar: DAY 4
9 | Test case writing for New Job Functionality Page | bar: DAY 5 to DAY 6
10 | Test case writing for Report Page | bar: DAY 7
11 | Next Sprint Planing | bar: DAY 9

## Sprint-1
30March - 10 April
TASK # | DESCRIPTION | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10
1 | Creation of HTML and CSS for landing page | bar: DAY 1 to DAY 3
2 | Creation of HTML and CSS for widget page | bar: DAY 3 to DAY 5
3 | Start the application development
4 | Design for report pages | bar: DAY 6 to DAY 8
5 | Preparing TestPlan | bar: DAY 1 to DAY 3
6 | Identifying Test Scenarios as per the Requirement | DAY 1: Spill over
7 | Start writing testcases based upon the Test Scenarios | DAY 1: Spill over
8 | Gathered requirements for cluster functionality | bar: DAY 1 to DAY 4
9 | Identified the backlog items based on the requirements gathered | bar: DAY 2 to DAY 6
10 | Created backlog items in VersionOne | bar: DAY 5 to DAY 7
11 | Estimated the backlog items based on the bandwidth | bar: DAY 5
12 | Assigned the items to individuals | bar: DAY 5
13 | Backlog is almost freezed | bar: DAY 10
14 | Created the design documents with wireframes attached | bar: DAY 5 to DAY 7
15 | Test case templation creation is done | bar: DAY 2
16 | Test plan creation is done | bar: DAY 4 to DAY 8

## Sprint-0
16-27th March
TASK # | DESCRIPTION | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10
1 | Installation of Ubuntu OS and Jumbune Activation | bar: DAY 1 to DAY 2
2 | Go through the Jumbune Videos and Requirements Gathering and Analysis | bar: DAY 2 to DAY 3
3 | Proposal of deliverables | bar: DAY 4
4 | Proposal of design - Rough Designs/Wireframes | bar: DAY 5
5 | Requirement gathering and analysis. | bar: DAY 5 to DAY 8
6 | Area/scope of Testing | bar: DAY 8 to DAY 9
7 | Sample Testcase Template | bar: DAY 10